## Backlog
| Task | [11 empty] | Size | Story Point
| ID |  | Task Description |  |  | Acceptance Criteria | Task Name | Size | Priority | Status | Sprint | Notes | Large | 7~12
| TS1 |  | Project Start - group finalized 9/14/22 |  |  | Agreed by all team members | Project_groupForm | 5 | High | Done | 1 |  | Medium | 4~6
| TS2 |  | Pick Project Idea/ assign roles |  |  | Agreed by all team members | Project_setup | 7 | High | Done | 1 |  | Small | 1~3
| TS3 |  | Project Description/Statement/Scope |  |  | Approved by all team members | Project_proposal | 7 | High | Done | 1
| TS4 |  | Working Agreement |  |  | Agreed by all team members | Project_agreement | 7 | High | Done | 1
| TS5 |  | Build Wiki Page |  |  | Wiki page is will organized, shows all the information about the project | Project_wiki | 8 | High | Done | 1
| TS6 |  | Market Research |  |  | Agreed by all team members | Project_market | 4 | High | Done | 2
| TS7 |  | Establishment of techniques and tools |  |  | Agreed by all team members, and identify the type of technology or tool that will be used in each section | Project_toolsResearch | 7 | High | Done | 2
| TS8 |  | Define specific feature details |  |  | Approved by all team members | Project_define | 7 | High | Done | 2
| TS9 |  | API Research |  |  | Approved by all team members | Project_API | 3 | High | Done | 2
| TS10 |  | Design of User Stories & Other Tasks (Backlog-1/2) |  |  | Approved by all team members | Project_Backlog | 10 | High | Done | 2
| TS11 |  | Design Project Acceptance Criteria (Backlog-2/2) |  |  | Approved by all team members | Project_AC | 9 | High | Done | 2
| TS12 |  | Design Project Test Cases |  |  | Approved by all team members | Project_testCases | 8 | High | Done | 2
| TS13 |  | Design MVP prototypes and sketches |  |  | Approved by all team members | Project_MVPdesign | 9 | High | Done | 2
| TS14 |  | Design interactive interface with the user |  |  | Approved by all team members | Project_UIdesign | 9 | High | Done | 3 | added in 2022/11/01
| TS15 |  | Design Dashboard for the webApp that shows key information |  |  | Approved by all team members | Project_Dashboard | 9 | High | Done | 4 | added in 2022/11/28
User Story
Fall 22 - spring 23 | ID | As a... | As a... | I want to... | So that I can... | Acceptance Criteria (format: use keywords Given, When, Then) | Task Name | Size | Priority | Status | Sprint | Notes
| US1 | Retail Manager | Inventory Manager | I want to be able to add new inventory to my database | Keep my database accurate to my changing inventory | When a user adds data, Then the database will add a new row. | DBS_add | 4 | High | Done | 3
| US2 | Retail Manager | Inventory Manager | I want to be able to edit inventory items in my database | Make changes to inventory details and correct typos | When a user delete data, Then the database will delete the row. | DBS_edit | 4 | High | Done | 3
| US3 | Retail Manager | Inventory Manager | I want to be able to delete inventory items in my database | Effeciently utilize server space and keep data accurate | When a user edit data, Then the database will edit the row | DBS_delete | 4 | High | Done | 3
| US4 | Retail Manager | Inventory Manager | I need to sort the data from the database that is displayed on the page | analyze and track my inventory my different metrics | Given different categories, When the user selects a category, Then show the products undere that category. | DBS_sort | 4 | Medium | Done | 3
| US5 | Retail Manager | Retailers Manager | I want to be able to check my inventory with a visual chart | Get a clearer picture of my inventory | Given automatically generated charts, When the user changes the chart options or changes the data range, Then the chart is regenerated based on user behavior | DBS_visualization | 7 | High | Waiting | 5
| US6 | Retail Manager | Inventory Manager | I would like to be alerted when some items are out of stock | Replenish my inventory in a timely manner | When an item is about to expire, Then the system will automatically send a reminder. | DBS_alert | 5 | Medium | Waiting | 3
| US7 | Retail Manager | Inventory Manager | I want the system to record my sales and analyze them | Keep track of my sales and change sales strategies | Given users the opthon of AI analysis, When the user chooses to use this feature, Then the user's data is used as input for his analysis fuciton, Then provides analysis of the data, such as the history of sales for each item. | DBS_analyze | 10 | Medium | Waiting | 5
| US8 | Retail Manager | Retailers Manager | I want to be able to enter data via cell phone camera or code reader | Input data easily | Given barcode entry options, When the user enters product information using the barcode Then the corresponding product information, such as product name, brand, price, etc., is automatically populated. | DBS_barcodeInput | 9 | Medium | Done | 4
| US9 | Cashier | Inventory Manager / Cashier | I want to get the item information from online database | I don't need to type everything about the item manually | Given a item's barcode, When the barcode is scanned, Then the "add item" form is filled automatically | DBS_itemInfo | 7 | Medium | Done | 4
| US10 | Cashier | Cashier | I want to be able to calculate the amount of money owed | Know the total amount of money owed | When there are no items remaining to be added, Then the total amount of payment due will be correctly reported | CR_amountowed | 3 | High | Waiting | 5
| US11 | Cashier | Retailers Manager | I want to be able to record a payment | Collect money from the customer | When payment is tendered, Then the status of the order will change from "Payment Outstanding" to "Paid" | CR_deposit | 3 | High | Waiting | 5
| US12 | Cashier | Marketing Manager | I want to keep track of what items the customer wants to purchase | Analyze consumer preferences | Given a list of custmore, When select a customer, Then show the history of the customer | CR_trackCunsumer | 3 | High | Done | 4
| US13 | Cashier | Cashier | I want to record and offer a receipt of the customer's purchase | Have an itemized list of items purchased by the customer | When an order is paid, Then a formatted record of the sale will be created | CR_receipt | 12 | Low | Pending | 5 | changed story points
| US14 | Retailers Manager | Marketing Manager | Evaluate suppliers | Create relationships with the best possible suppliers for my industry | Given a list of all suppliers, When a user filters on a detaill, Then the relevant data will be shown | SRM_eval | 6 | High | Done | 3
| US15 | Retailers Manager | Marketing Manager | Streamline onboarding with suppliers | Quickly establish working supply chains | Given a new supplier, When new data needs to be collected, Then a standard template will be sent and uploaded to the database | SRM_select | 3 | High | Done | 3
| US16 | Retailers Manager | Marketing Manager | Manage supplier performance | Quickly and easily track supplier performance with key performance metrics that are already established for me | Given a supplier ID, When the metrics are requested, Then the database returns accurate data | SRM_kpi | 6 | Medium | Waiting |  | Suppliers evaluated and given selection scorecards (capacity, quality, performance, pricing historical, etc.)
| US17 | Marketing Manager | Marketing Manager | I want to upload my sales data | Track/Maintain/Organize my data | When i upload sales data, Then the database update to add | DBS_upload | 3 | High | Done | 4
| US18 | Marketing Manager | Marketing Manager | I want the model to forecast prices for items in my inventory | Reduce the uncertainty and guesswork in my pricing | Given a data set, When a forecast is run, Then a best fit price will be calculated | ML_predict | 12 | High | Waiting
| US19 | Marketing Manager | Marketing Manager | I want the model to predict total sales revenue by time period | Best serve my customers and maximize seasonal consumer trends | Given a data set in a timerange, When a forecast is run, Then total projected sales will be caclulated | ML_timepredict | 10 | low | Waiting
| US20 | Marketing Manager | Marketing Manager | I want the model to recommend quantities of products for sale | Be leaner in my logistics and maximize profits | Given a data set in a timerange, When a forecast is run, Then suggested total quantity of inventory will be calculated | ML_pricequantity | 12 | low | Waiting
| US21 | Logistics Manager | Retailers Manager | I want to check the detail of the current orders | Have idea of a order detail | Given information about all order. When the user selects a particular order, Then the details of that order are provided. | LOG_OrderDetails | 3 | High | Done | 4
| US22 | Logistics Manager | Retailers Manager | I want to get notification when delivery of an order is imminent | Be prepared for the coming package | Given information about all logistics. When the user selects a particular logistics, Then the details of that logistics are provided. | LOG_comingTrack | 6 | Medium | Done | 4
| US23 | Logistics Manager | Retailers Manager | I want to check the previous shipping information | Ensure accurate shipping details | When shipping details are entered, Then a check against the previous details is run | LOG_history | 5 | low | Done | 4
| US24 | Logistics Manager | Retailers Manager | I want to see shipping history filtered for specific details | Review and analyze my shipment effeciency and timeliness | When a filter is added, Then data matching that filter is returned | LOG_filter | 3 | Medium | Done | 4
| US25 | Systems Security | Retailers Manager | I want to use two factor authorization to verify my customer's login | Prevent fraudulent login | Given a new device, When login is successful, Then the secondary security check will be sent | Login_2Factor | 4 | Medium | Pending | 4
| US26 | Systems Security | Retailers Manager | I want to strongly encrypt and safely store my user's data | Ensure my customers their data is safe | Given a database of customer data, When unauthorized entry is attempted, Then request will not be returned | DBS_security | 3 | Medium | Done | 4
| US27 | Systems Security | Retailers Manager | I want to be able to access my data from any device | Know the status of my business anytime, anywhere | Given successful login from a device, When access is attempted, Then the app is correctly rendered | DBS_cloud | 3 | High | Done | 3

## Test Cases
ID | User Story | Test Description | Test Date | Action | Expected Output | Actual Output | Test Result (Pass/Total) | Comments
T1 | US1 | Insert a product data | 2022-11-13 | Enter product info(price, description...) | Product data is correctly displayed in the database | New item shown in the database | 3 of 3
T2 | US2 | Edit a product data | 2022-11-13 | Change the price. update the image, re-write the description | Product database is updated with new data | Updated item info is shown in the database | 3 of 3
T3 | US3 | Delete a product data | 2022-11-13 | Delete a product | The target data is deleted | The target item is deleteed | 3 of 3
T4 | US4 | Sort the data | 2022-11-13 | Select Classification = food | all food items are display | all food items are display | 3 of 3 | This project will need to be retested in the future. We should have a drop down list for users to select categories instead of manually typing
T5 | US16 | Evaluate suppliers | 2022-11-13 | Select supplier which id=1 | all info of supplier is shown | all info of supplier is shown | 3 of 3
T6 | US17 | Collect supplier's info | 2022-11-13 | Add a new supplier to the DBS | a new supplier info is added | shows the info of the new supplier | 3 of 3
T7 | US31 | Online realtime Database | 2022-11-13 | Add a new item data from device A, and check the update from device B | the new item is shown on device B | the new item is shown on device B | 3 of 3
T8 | US5 | Visualize data |  | Renders the output page of the imported database combined with the graph | For example, a pie chart (the proportion of each product, the quantity is clearly marked)
T9 | US6 | Set up cargo replenishment reminders |  | Alerts are sent when the product falls below the set quantity | When the number of products is less than or equal to 10, the out-of-stock status will be displayed
T10 | US7 | Intelligent analysis of sales status |  | After inputting data, intelligently analyze the sales method and make decisions based on sales records. | AI gives a suggestion
T11 | US8 | Scan barcode | 2022-12-10 | Barcode recognition by camera | Output the data contained in the barcode | The barcode numbers | 8 of 10 | Need HD webcam for better result
T12 | US9 | Scan product | 2022-12-14 | Identify and add items via camera | Add the item to the bill | The item INFO is automatically filled into the form | 10 of 15 | Some item is not found in the database
T13 | US10 | After stopping adding goods, produce a total price |  | Calculate the sum of the total price after multiplying the unit price and quantity of each item | Total amount owed=Specific amount (40 $)
T14 | US11 | Navigate to the record the payment |  | Load the payment page, confirm the payment and display the payment | Load paid page
T15 | US12 | Generate customer list and scroll through the form | 2022-12-05 | Navigate to the customer list, and click to view the details of each line of customer history | Each customer history record in the list can be clicked. Click a customer history record randomly to navigate to the history details page | A list of customers | 3 of 3
T16 | US13 | Generate & print the invoice |  | Input orders' detail | Gnerate a receipt for the orders
T17 | US14 | Provide the name list of suppliers | 2022-12-05 | Navigate to the supplier list and display some basic information. For example, name, main industry, etc. Users can click the supplier to obtain more details. | View the name of each supplier, and click a supplier to view its details.
T18 | US15 | regular template |  | When import new data, provide a general template(including name, price, quantity, type, saving time, etc.) | This interface can generate a standard template
T19 | US16 | Filter Index |  | Set suppliers ID, evaluate and so on. (Used to filter user needs) | This interface displays some public data of the supplier on business cooperation, such as performance
T20 | US17 | Upload, update data |  | Upload local data and update it to the database | After the local data is uploaded, the database is updated and new data information can be viewed | New data is shown | 3 of 3
T21 | US18 | Forecast inventory price |  | Obtain a specific price according to the inventory quantity or mathematical function model | Output an estimated price
T22 | US19 | Total forecast sales |  | Based on the current time or quarter, the sales volume in this period can be estimated (through the previous data model) | Output an estimated quantity
T23 | US20 | Number of products recommended for sale |  | (Based on previous data or mathematical model) speculate the sales quantity of the goods to maximize the benefits within a limited time | Output an estimated range
T24 | US21 | Logistics transportation status management |  | Navigate to the logistics of the item, provide the date and location, and predict when it will arrive | The status of the article (shipped or not shipped), information about the goods, date, and location | The UPS shipment INFO is shown | 4 of 5 | only works for UPS shipments
T25 | US22 | Logistics arrival management |  | When the goods are about to arrive, the recipient will receive a prompt from the app | Pop up window with prompt (SMS or email or other methods) | A message is shown | 5 of 5
T26 | US23 | Logistics History |  | Navigate to the logistics history page. Each history is a separate information, record date, recipient, sender, bill of lading number, goods information, etc | The latest historical data are arranged from top to bottom, and you can view the details of each historical data | A list of all the shipments | 3 of 3
T27 | US24 | Logistics History Filter Settings |  | This setting has specific filtering information, such as keywords, dates, logistics, etc | After selecting filtering information, jump to the page with relevant data | Filtered data is displayed | 3 of 3
T28 | US25 | Double layer security verification |  | Pop up authentication protection pop-up settings | The user is required to enter the verification code (version 1) or the verification code sent to the mobile phone or email (version 2)
T29 | US26 | Cloud data security management |  | When viewing the uploaded data, you need to set a password (including numbers, letters, etc.) for the first time, and the password can be changed. You need to enter the password every time you view the uploaded data | Enter the password, or change the password from an existing password. Assumption (if the input error exceeds 3 times, it will be locked)
T30 | US27 | User account password setting |  | Set the login interface. The data of each user is not interconnected. Enter the account password and log in to your own account | Login interface, account, password, forgotten password, login button. Can log in after input